As of March 27, 2009

Proposed Next Steps

Deadline		Task

March 27		Review work of March 20			All

April 3 (1)		Review work					All

Identify new student members			Wendy

Consult with Student Activities

April 10 (2)		Review work					All

April 17 (3)		Share data from survey				Andi

Clean-up/Review

April 24 (4)		Vetting	 Process

Experts & Attorney

May 1 (5)		Vetting Process

Forums

May 8 (6)		Vetting Process

May 15 (7)		Vetting Process

May 22 (8)		Review feedback

Revise recommendations

May 29 (9)		Finalize recommendations

June 5 (10)		Submit recommendations to VPSA

September 23 (4)	Hold Public Hearing

January 1, 2010		New code in effect

Vetting Process

Forums – week of May 1

May 6, Noon

May 5, 4-6 pm

Broad call for feedback – deadline May 13

TESC Crier – post 4/28 and 5/5

All Faculty & Staff DL – post 4/28 and 5/5

Direct input sought from:

Geoduck Union (Wednesday meetings—5/6

and 5/13)

Faculty  (4/22 meeting, 5/6 meeting)

Academic Deans (Tuesday meetings—5/5 &

5/12)

Student Affairs Staff

Policy Review Committee

Student Activities student coordinators

Academic Peer Adviors

Targeted program faculty/students

Conduct affiliates

Police Services

RAD Staff

Joe Tougas

Helena Meyers-Knapp

Julie Slone

AmyLyn Ribera

Tracey Johnson

Art Costantino