## Slide 1: Dredged Sediment and Liquid Addition Research, Development and Demonstration Project

## Slide 2: Organization of Presentation
Introduction
Operation Plan/Proposed Methods of Liquid Addition
Engineering Analysis
Monitoring
Data Analysis and Reporting
Conclusions

## Slide 3: Introduction

## Slide 4: Introduction
Research, Development and Demonstration (RD&D) project
  Add dredged sediment and liquid to the landfill
  Recently received permit from ODEQ for 3-year
  Allows us to demonstrate that operations can be carried out and objectives achieved with no increased risk to human health and the environment
  Permit can be renewed for up to a total of 12 years
  With positive results, hope to convert to a permanent operating practice

## Slide 5: Demonstration Period
Maximum Permit Duration Is 3 Years
Possibility to Extend for Additional 9 Years
To Get Extensions, Need to Show:
  Results
  Good Data Collection and Analysis
  Careful Operations
  “No Increased Risk”

## Slide 6: Why Add Moisture to the Landfill?
Increase the rate of decomposition of the waste
Environmental Benefits
  Primary Benefits
    Increased gas generation rate
      Improve economics of landfill gas power plant project
  Reduced stabilization period of the waste
    Groundwater Contamination
  Reduced groundwater use
    Dust control with leachate instead of groundwater

## Slide 7: Why Add Moisture to the Landfill?
Secondary Benefits
  Conservation of land
    Can put more waste in the same airspace
  Reduced daily and intermediate cover soil use
    Use as ADC - pending DEQ approval
  Improved litter control
    Less blowing litter
  Environmentally safe disposal option for liquid wastes

## Slide 8: Why Didn’t We Do This Before?
1980’s State of the Art
  Keep the waste as dry as possible
  Minimize leachate generation
2003 State of the Art
  Add liquid to waste to accelerate decomposition and gas generation
  Recirculate leachate
  Reduce the long term risk that the solid waste poses to the environment

## Slide 9: Why the Change?
Subtitle D base liners and leachate collection systems are the difference
  Prevent leakage of leachate into the environment
Old landfills didn’t have good liners and leachate collection systems
  If liquid entered the landfill, it seeped through and contaminated the groundwater
  Adding liquid to landfill to increase degradation would also increase groundwater contamination
    Benefits not worth the cost

## Slide 10: How Much Liquid Do We Need?
Waste at Columbia Ridge has lower moisture content than average landfill because of arid climate
  Maybe 20% water
Bioreactor
  Waste moisture content = 40% or more
  Extremely rapid decomposition
  Gas generation within weeks of waste placement
  Complete degradation in months or a few years

## Slide 11: How Much Liquid Do We Need?
Wet conventional landfill
  Less than 40% moisture …
    … but more than “dry” landfill
  Increased decomposition and gas generation
  Initial step at Columbia Ridge
  If this step is successful, may convert into bioreactor later

## Slide 12: Operation Plan Methods of Liquid Addition

## Slide 13: Sources of Liquid
Dredged Sediment
  Contaminated soil at the bottom of harbors, rivers, lakes
  Excavated/dredged (along with some water) by contractors as part of environmental cleanup projects
Leachate from the landfill
  Stored in the leachate evaporation pond
Surface water collected at the landfill
  To be collected in ponds excavated outside the footprint of the landfill

## Slide 14: Sources of Liquid
Commercial Liquids
  Need DEQ approval as special waste
    Biosolids
    Port-o-let wastes
    Tank farm rainwater
    Off-spec beverage wastes (soft drinks, beer, mouthwash)
    Water based printing water
    Leachate from other landfills

## Slide 15: Waste Stream Screening Process
Dredged sediment and commercial liquids are accepted as special wastes
Send notification to DEQ after waste passes special waste screening but before waste is accepted

## Slide 16: Waste Stream Screening Process
Need to screen for liquids that could harm methane generation
  pH less than 6
  High concentrations of metals
    TCLP metals above RCRA limits
    Iron > 20,000 ppm
    Zinc > 5,000 ppm
  Total petroleum hydrocarbons > 3,000 ppm
  Nitrates > 500 ppm
  COD or BOD > 300,000 ppm
  Special waste program has been modified to include these criteria
    Approved By ODEQl

## Slide 17: Quantity of Liquids and Timing
Dredged Sediment
  Can only be dredged during “fish windows”
    Between approx. August 1 and February 1
    Initial estimate of approximately 750,000 tons/year
      Based on upcoming dredging projects on the horizon
      750,000 tons/year = 5,000 tons/day during the fish windows
Leachate recirculation, stored runoff, and commercial liquids
  Leachate (on-site): approximately 3,900 gallons/day, year-round
  Stored runoff: depends on rainfall, maybe 2 million gallons, year-round but primarily during rainy season,
  Commercial liquids: quantity to be determined, accepted year-round

## Slide 18: Locations and Methods of Waste Placement/Liquid Addition
Dredged Sediment
  Co-disposal at the working face
    Preferred Method
    If working face becomes too wet, then will use other methods
  Placement in infiltration basins built into the waste
    Depressions built into the waste by operations
    Size and depth to be determined
    On top of hill, not on slopes
      100 ft. min from exterior slopes
      20 ft. min. refuse beneath basin

## Slide 19: Locations and Methods of Waste Placement/Liquid Addition
Dredged Sediment
  Placement Above Intermediate Cover on Sideslopes
    Permitted to place on sideslopes in lifts up to 5-feet thick
      After water in sediment seeps into landfill, may go back and excavate dried sediment to use as ADC
      Pending approval by DEQ
      Need to remove all but 6-inches of int. cover first

## Slide 20: Locations and Methods of Waste Placement/Liquid Addition
Leachate, stored runoff, and commercial liquids
  Typically added at working face or on top of completed lift before intermediate cover is placed
  Typically brought to working face in tanker trucks
  May also use temporary pipelines for leachate and stored runoff
  Permitted to do spray application of piped liquids
  Permitted to use leachate to water roads
    Only roads within the limit of waste!!
  Liquid added to working face “consistent with best industrial hygiene practices and protective of employee health and safety.”

## Slide 21: Termination of Liquid Addition
DEQ driven - if monitoring data shows that a method of liquid addition is increasing risk to human health and environment, stop that method until the risk can be eliminated
Operations driven – operational constraints such as wet conditions, equipment shortage, etc.
  Will resume at ops manager’s direction

## Slide 22: Engineering Analysis

## Slide 23: Engineering Analysis
In-place waste and sediment physical properties
  Moisture content of waste: approx. 20%
  Moisture content of sediment: approx. 40%
Capacity to accept dredged sediment and liquids
  Water balance and waste absorptive capacity
    Absorptive capacity (field capacity) of waste
      Amount of liquid waste can absorb before leachate starts to drain out of it
      Sponge or paper towel comparison

## Slide 24: Engineering Analysis
  Absorptive capacity of waste at Columbia Ridge is approx. 37.4 gallons/ton
  Absorptive capacity of waste in place is approx. 767,000,000 gallons (based on 20.5 million tons in place)
    Very conservative estimate
    Could be 2 to 3 times this number
  The Message
    Will be very hard to add enough liquid to exceed absorptive capacity of the waste

## Slide 25: Engineering Analysis
  Sideslope Application
    Potential for “short circuiting” in areas where waste is not deep
      Liquid finds an open flowpath in the waste and flows directly to leachate collection system
    Placement restrictions to prevent short-circuiting
      No sediment or other liquids placed in areas:
        With less than 20 feet of waste
        Within 30 feet (horizontally) of limit of waste
        If slope is 4:1, 30 feet horiz = 8 – 10’ vertically from bottom of slope

## Slide 26: Engineering Analysis
Maximum quantities to be accepted based on leachate collection system capacity
  Need to maintain leachate level on base liner less than 1-foot deep
  Calculated maximum quantity of sediment to be placed in an area and still maintain leachate compliance depth
    5.4 million gallons per acre, or
    123,000 tons dredged sediment per acre
  Not the limiting factor

## Slide 27: Slope Stability
Adding too much liquid or dredged sediment near intermediate waste slopes can make slopes unstable
  Calculations done to evaluate:
    5,000 tons/day disposed at working face – OK
    5-foot layer on sideslopes – OK

## Slide 28: Leachate Collection System
Liquid Capacity
Filter Geotextile Performance
Pipe Strength and Deflection Analysis
Geotextile Cushion

## Slide 29: Settlement
Settlement of Base Grades
Settlement of Refuse

## Slide 30: Runoff From Sediment
No liquid is expected to run off from sediment placed on the sideslopes
Most will evaporate
Some will infiltrate into waste

## Slide 31: Landfill Gas
Gas flow rate comparison
  Columbia Ridge is generating much less gas than similar landfills in wetter climates
  Methane producing bacteria don’t have enough moisture to thrive

## Slide 32: Landfill Gas
Effects of additional moisture
  Additional moisture will…
    Increase methane producing bacteria, which will…
    Increase rate of waste decomposition, which will…
    Increase rate of gas generation

## Slide 33: Landfill Gas
  Which Will…
    Stabilize the waste sooner
      Reduces post-closure risks and costs
        Groundwater Contamination,
        Gas Migration,
        Cover repair due to settlement
      Allows more waste to be placed in the same airspace
    Improve the economics of a landfill gas power plant
      More gas is generated over a shorter period of time
      Allows size of power plant to be increased, which improves economics

## Slide 34: Landfill Gas
Gas collection system design
  NSPS regulations still apply
  Still install wells after waste has been in place for 5 years
  Surface scans must still be below 500 ppm
Gas collection system installation timeline
  Additional wells and header being installed in next few months to comply with NSPS If gas generation rate increases significantly, may have to install additional wells before required by NSPS timeline
  Monitoring program (discussed soon) will determine this

## Slide 35: Landfill Gas
  Proposed alternate NSPS well installation timeline
    Install gas wells only if monitoring data indicates that stable methanogenesis has been reached
    Methanogenesis – stage of waste decomposition when methane is produced
    May be more than 5 years based on current gas monitoring data
  Still needs to be approved by DEQ air quality division

## Slide 36: Landfill Gas
Landfill gas beneficial re-use timeline
  Primary benefit of adding moisture to waste → enhanced gas generation
  Should make construction of a power plant or other beneficial re-use project economically viable sooner than if moisture addition did not occur
  Columbia ridge has committed to preparing a technical and economic feasibility study for a beneficial re-use project within 120 days of permit date

## Slide 37: Monitoring: Demonstrating That It’s Working

## Slide 38: Monitoring
Very important component of project
  DEQ wants to see evidence that liquid addition is resulting in the environmental benefits
  Will also ensure that there is no increased risk to human health and the environment
Stability
  Leachate Seeps
    Can be an indicator that an area of the landfill has become saturated
    Monitor sideslopes where liquid addition is occurring weekly
    Monitor sideslopes where sediment has been placed for locations where sediment is not drying as quickly as other areas
      Could be an indication of a seep under the sediment

## Slide 39: Monitoring
Leachate collection system
  Leachate Genaration
    Continue to monitor leachate flow weekly at pond
    Additional monitoring points will be added
  Leachate Head
    Continue to monitor per current schedule
    Monitor at north end of landfill and at north end of modules 6 and 9 (temporary leachate header)

## Slide 40: Monitoring
Leachate Quality
  Quarterly Monitoring
  Parameters to Monitor:
    COD
    BOD
    Temperature
    Ph
    Volatile Organic Acids
  Compare to pre-liquid addition results
  Monitoring starts 4th quarter (now)

## Slide 41: Monitoring
Integrity of leachate collection pipes
  Purpose: demonstrate that pipes are not clogged and can still function as intended
  Video inspection of select pipes, or other methods, if available
  Required once during the 3-year permit period
  Probably near end of permit period to show that liquid addition hasn’t impacted pipes
  May need to do additional inspection now to use as baseline for comparison

## Slide 42: Biostabilization Monitoring
Also known as waste degradation
Parameters to measure
  Temperature
  Moisture Content
  Ph
  Organic Solids

## Slide 43: Biostabilization Monitoring
Measurement Locations
  Test Pits
    Excavate in areas where liquid addition is occurring and gas well drilling is not planned in near future
      Working face do-disposal,
      Infiltration basin, and
      Sideslope sediment application area
    Control Areas
      Where liquid addition has not been occurring
      To use for comparison

## Slide 44: Biostabilization Monitoring
  Gas Wells’
    All parameters - during drilling
    Temperature only - after installation
      Part of monthly NSPS requirement
  Test Pit Frequency
    At least once during permit period
      Excavate near end of permit period to best assess degree of degradation during that time
      2003 and early 2004 gas well drilling should provide baseline waste data without having to excavate test pits

## Slide 45: Biostabilization Monitoring
Waste Settlement
  Annual aerial mapping, or
  Ground surveys
  Calculate waste settlement and waste density

## Slide 46: Landfill Gas Monitoring
General
  In accordance with NSPS
  Several alternative monitoring protocols proposed, but still need to be approved by DEQ air quality
Surface Scans
  Continue to perform quarterly surface scans per NSPS
  Install temporary methane monitoring probes in areas exceeding 500 ppm
    Measure methane and carbon dioxide monthly at 5 foot intervals in probes

## Slide 47: Landfill Gas Monitoring
Gas Quality
  Monitor wells monthly once wells indicate that steady-state methanogenesis has been reached
Gas Quantity
  Measure monthly at each well
  Measure monthly at flare
  Compare to historical data to look for increasing gas flow due to liquid addition
  Calculate gas generation rate from each well annually

## Slide 48: Landfill Gas Monitoring
Well Performance
  Measure liquid levels in gas wells in areas where liquid addition is occurring
  Twice Per Year
  If high liquid levels are consistently found in wells, stop liquid addition in that area

## Slide 49: Modification of Monitoring Program
Flexibility
  Latitude to make changes in monitoring program based on data collected
Letter notification to DEQ

## Slide 50: Data Analysis and Reporting

## Slide 51: Data Analysis and Reporting
Water balance calculation
  Perform Annually
  Submit with annual report
Annual Report
  Submit to DEQ by June 15th each year
    Data through April 30 of that year
  Summarize RD&D activities
    Data Collected
    RD&D Operations
    Lessons Learned
    Conclusions Drawn, and
    Goals Achieved

## Slide 52: Data Analysis and Reporting
  Specific information to include in report
    Overall quantity of sediment and liquid added to the landfill;
    Physical properties of the sediment and liquids added to the landfill;
    Locations of sediment and liquid addition;
    Ratio of sediment to msw placed at working face for various operating conditions;
    Assessment of various sediment placement methods and discussion of optimum methods of increasing moisture content of the waste mass;

## Slide 53: Data Analysis and Reporting
  Specific information to include in report (con’t.)
    Estimate of liquid added to the landfill:
      Moisture added to the waste mass by placing sediment and liquid into the MSW at the working face;
      Moisture that has drained from the dredged material placed on intermediate cover and infiltrated into the underlying waste;
      Moisture added to the waste mass from leachate, stormwater, and other liquids

## Slide 54: Data Analysis and Reporting
  Specific information to include in report (con’t.)
    Estimate of remaining absorptive capacity of the waste mass;
    Estimate of groundwater saved due to use of other liquids for dust control;
    Amount of additional leachate generated due to the addition of the liquids;
    Comparison of leachate, landfill gas, and waste settlement data to historical data
      Determine the effects, if any, of moisture enhancement provided by the sediment and liquids;

## Slide 55: Data Analysis and Reporting
  Specific information to include in report (con’t.)
    Leacahate seeps caused by RD&D activities
    Results of leachate head and flow rate measurements
    Results of leachate pipe inspections
    Results of surface scans and other landfill gas monitoring
    Estimate of state of methanogenesis of waste within the landfill
    Estimate of when a gas collection system will be required in specific areas based on actual gas generation rate and surface scan results; And
    Assessment of the monitoring program
      Discussion of changes implemented, and
      Changes anticipated for the coming year

## Slide 56: Data Analysis and Reporting
Conclusions
  Report will assess whether the RD&D project goals are being achieved at “no increased risk to human health and the environment.”

## Slide 57: Conclusions

## Slide 58: Conclusions
Benefits
  Accelerate Waste Stabilization
  Accelerate Gas Generation
  Improve economics of landfill gas power plant
  Reduce Groundwater Use
  Reduce Dust
  New waste stream, increased revenue, more jobs